## Raw Data
S No | Date | Change ID | Impact | Circle | Domain | Parent Category | Child Category | Summary | Change Request Status | Planned Count | Done Count | Closure Comment | Vendor | Scheduled Start Date | Scheduled End Date | Execution Type
1 | 25-Oct | CRQ000004348878 | 2-Significant/Large | CH | RAN-Cell | Capacity Addition | License Addition | 4G H// Enodeb License Loading 170 node | Completed | 170 | 170 | Completed Successfully | Huawei | 2023-10-26 | 2023-10-26 06:00 | Manual Execution
2 | 20-Oct | CRQ000004352695 | 2-Significant/Large | UPE | RAN-Cell | Optimization | HO/NBR Opt | ADJL Creation CRF | Completed | 143 | 100 | Completed Successfully | Nokia | 2023-10-21 | 2023-10-21 06:00 | Manual Execution
3 | 20-Oct | CRQ000004354152 | 2-Significant/Large | UPE | RAN-Cell | Optimization | Parametric Changes | TD_DC_DEGROW | Completed | 25 | 24 | Completed Partially/plan failed in some nodes | Nokia | 2023-10-21 | 2023-10-21 06:00 | Manual Execution
4 | 20-Oct | CRQ000004365374 | 2-Significant/Large | RJ | RAN-Cell | Traffic Balancing | Traffic Migration | CR for POP traffic Shifting for 2G Nodes | Completed |  | 24 | Completed Successfully | Ericsson | 2023-10-20 11:00 | 2023-10-20 18:00 | Manual Execution
5 | 23-Oct | CRQ000004366722 | 2-Significant/Large | MU | RAN-Cell | Others | Site Nomenclature Change | LTE Cell Name Change | Completed | 300 | 300 | Completed Successfully | Nokia | 2023-10-23 07:00 | 2023-10-23 23:00 | Manual Execution
6 | 25-Oct | CRQ000004366740 | 2-Significant/Large | MU | RAN-Cell | Trail | Parameter | 5G NRCELL PARAMETER CHANGE_NR-dlDataSplitMode -Trial_Independent Parameter | Completed | 37 | 37 | Completed Successfully | Nokia | 2023-10-26 01:00 | 2023-10-26 06:00 | Auto Execution
7 | 25-Oct | CRQ000004366893 | 2-Significant/Large | MU | RAN-Cell | Optimization | Parametric Changes | DSS Implementation | Completed | 213 | 215 | Completed partially_two sites reverted | Nokia | 2023-10-26 01:00 | 2023-10-26 06:00 | Manual Execution
8 | 20-Oct | CRQ000004367254 | 2-Significant/Large | DL | RAN-Cell | Transport | IP Addition | 4G site/POP Shifting | Completed |  | 50 | Completed Successfully | Ericsson | 2023-10-20 10:00 | 2023-10-20 23:00 | Manual Execution
9 | 23-Oct | CRQ000004367320 | 2-Significant/Large | UPW | RAN-Cell | Transport | IP Addition | 4G And 2G Sites POP Shifting in Ericsson Node | Completed |  | 43 | Completed Successfully | Ericsson | 2023-10-23 10:00 | 2023-10-23 22:00 | Manual Execution
10 | 20-Oct | CRQ000004367327 | 2-Significant/Large | UPW | RAN-Cell | Traffic Balancing | BSS Load Balancing | 4G POP Shifting in Huawei Node | Completed |  | 21 | Partially Done | Huawei | 2023-10-21 | 2023-10-21 06:00 | Manual Execution
11 | 25-Oct | CRQ000004367991 | 2-Significant/Large | KL | RAN-Cell | Capacity Addition | New Node Addition | CGI Creation for New Site in 6 MSCs | Completed | 6 | 6 | Completed Successfully | Ericsson | 2023-10-25 23:00 | 2023-10-26 06:00 | Manual Execution
12 | 20-Oct | CRQ000004368517 | 2-Significant/Large | HR | RAN-Cell | Transport | Traffic Offloading | Global: 4G/2G Sites traffic shifting from one pop to another | Completed |  | 20 | Completed Successfully | Ericsson | 2023-10-20 10:00 | 2023-10-20 19:00 | Manual Execution
13 | 20-Oct | CRQ000004369643 | 2-Significant/Large | AS | RAN-Cell | Transport | Traffic Offloading | Global CR for Pop shifting of 2G sites | Completed |  | 40 | Completed Successfully | Ericsson | 2023-10-20 11:00 | 2023-10-20 19:00 | Manual Execution
14 | 26-Oct | CRQ000004370240 | 2-Significant/Large | KK | RAN-Cell | Optimization | HO/NBR Opt | Cell ID Change and Ext Neighbor definition for 2G Swap Site | Completed |  | 50 | Completed Successfully | Huawei | 2023-10-26 23:00 | 2023-10-27 07:00 | Manual Execution
15 | 25-Oct | CRQ000004370392 | 2-Significant/Large | RJ | RAN-Cell | Optimization | Parametric Changes | LTE CR for dummy frequency deletion | Completed | 729 | 634 | partial completed | Ericsson | 2023-10-26 | 2023-10-26 06:00 | Partial Auto Execution
16 | 20-Oct | CRQ000004370714 | 2-Significant/Large | BH | RAN-Cell | Transport | IP Addition | LNMME IP addition_Independent parameter | Completed | 3000 | 2525 | PARTIALLY DONE DUE TO PLAN FAILED ON SOME NODES | Nokia | 2023-10-21 | 2023-10-21 06:00 | Manual Execution
17 | 20-Oct | CRQ000004370716 | 2-Significant/Large | BH | RAN-Cell | Transport | IP Addition | LNMME IP addition_Independent parameter | Completed | 3000 | 2826 | PARTIALLY DONE DUE TO PLAN FAILED ON SOME NODES | Nokia | 2023-10-21 | 2023-10-21 06:00 | Manual Execution
18 | 20-Oct | CRQ000004370730 | 2-Significant/Large | BH | RAN-Cell | Transport | IP Addition | LNMME IP addition_Independent parameter | Completed | 3000 | 2825 | PARTIALLY DONE DUE TO PLAN FAILED ON SOME NODES | Nokia | 2023-10-21 | 2023-10-21 06:00 | Manual Execution
19 | 20-Oct | CRQ000004370991 | 2-Significant/Large | OR | RAN-Cell | Optimization | Parametric Changes | 2G_BTS HOC POC PARAMETER CHANGES | Completed | 2000 | 3000 | Completed Successfully | Nokia | 2023-10-21 | 2023-10-21 06:00 | Manual Execution
20 | 20-Oct | CRQ000004371232 | 2-Significant/Large | CH | RAN-Cell | Others | Migration | 4G_Ericsson CVLAN & IP change migration(POP migration activity)Ericsson) | Completed |  | 40 | Completed Successfully | Ericsson | 2023-10-20 23:00 | 2023-10-21 06:00 | Manual Execution
21 | 20-Oct | CRQ000004372462 | 2-Significant/Large | GJ | RAN-Cell | Optimization | Soft Opt. TAC/LAC | TAC Changes_LTE | Completed | 80 | 80 | Completed Successfully | Nokia | 2023-10-21 | 2023-10-21 06:00 | Manual Execution
22 | 23-Oct | CRQ000004372672 | 2-Significant/Large | KK | RAN-Cell | Transport | Traffic Offloading | POP Migration Activity-OM | Completed |  | 50 | Completed Successfully | Huawei | 2023-10-23 23:00 | 2023-10-24 06:00 | Manual Execution
23 | 20-Oct | CRQ000004372720 | 2-Significant/Large | HR | RAN-Cell | Traffic Balancing | Traffic Migration | SNMPV2/V3 mo Creation and IP Correction in eNodBOTN (OSS) | Completed |  | 500 | Completed Partially | Ericsson | 2023-10-21 | 2023-10-21 06:00 | Manual Execution
24 | 20-Oct | CRQ000004372748 | 2-Significant/Large | UPW | RAN-Cell | Optimization | Parametric Changes | L2100 swap from Huawei to Ericsson Neighbor refresh | Completed |  | 973 | Completed Successfully | Huawei | 2023-10-21 | 2023-10-21 06:00 | Manual Execution
25 | 20-Oct | CRQ000004372800 | 2-Significant/Large | MH | RAN-Cell | Others | Migration | 2G SITE CREATION REQUIRED FOR REHOMING ¦BSC DISMANTLE:MAH | Completed | 45 | 45 | Completed Successfully | Nokia | 2023-10-20 08:00 | 2023-10-20 22:00 | Manual Execution
26 | 26-Oct | CRQ000004372838 | 2-Significant/Large | TN | RAN-Cell | Others | Migration | 2G_Ericsson CVLAN & IP change migration(POP migration activity)Ericsson) | Completed | 7 | 7 | Completed Successfully | Ericsson | 2023-10-26 23:00 | 2023-10-27 06:00 | Manual Execution
27 | 25-Oct | CRQ000004372941 | 2-Significant/Large | TN | RAN-Cell | Others | Migration | 2G_Ericsson CVLAN & IP change migration(POP migration activity)Ericsson) | Completed |  | 80 | Completed Successfully | Ericsson | 2023-10-25 23:00 | 2023-10-26 06:00 | Manual Execution
28 | 23-Oct | CRQ000004372946 | 2-Significant/Large | BH | RAN-Cell | Optimization | Parametric Changes | LTE Parameter Change(LNCEL3)_Independent Parameter | Completed | 2700 | 5790 | Completed Successfully | Nokia | 2023-10-24 | 2023-10-24 06:00 | Manual Execution
29 | 20-Oct | CRQ000004372958 | 2-Significant/Large | TN | RAN-Cell | Optimization | Parametric Changes | E// 4G Ducting Parameter Tuning in TN Ericsson Nodes | Completed |  | 1480 | Completed Partially | Ericsson | 2023-10-21 | 2023-10-21 07:00 | Manual Execution
30 | 20-Oct | CRQ000004372968 | 2-Significant/Large | RJ | RAN-Cell | Traffic Balancing | Soft Changes - 5G | 5G_readiness CR for Parameter Change (Ericsson)(5G_GUtranFreqRelationDefination) | Completed |  | 143 | Completed Partially | Ericsson | 2023-10-21 | 2023-10-21 06:00 | Manual Execution
31 | 20-Oct | CRQ000004373014 | 2-Significant/Large | OR | RAN-Cell | Optimization | Parametric Changes-5G | 5G parameter change_ Independent Parameter | Completed | 283 | 319 | Completed Successfully | Nokia | 2023-10-21 | 2023-10-21 06:00 | Manual Execution
32 | 20-Oct | CRQ000004373063 | 2-Significant/Large | CH | RAN-Cell | Optimization | Parametric Changes | 4G E// UL Trigger Mobility 1063 node | Completed |  | 1063 | partial Done | Ericsson | 2023-10-21 | 2023-10-21 06:00 | Auto Execution
33 | 26-Oct | CRQ000004373134 | 2-Significant/Large | KK | RAN-Cell | Traffic Balancing | Soft Changes | UL performance improvement Feature_Gulbarga | Completed |  | 269 | Completed Successfully | Ericsson | 2023-10-26 23:00 | 2023-10-27 07:00 | Partial Auto Execution
34 | 26-Oct | CRQ000004373228 | 2-Significant/Large | KK | RAN-Cell | Transport | Traffic Offloading | POP Migration Activity-2G | Completed |  | 50 | Partially Done | Huawei | 2023-10-26 23:00 | 2023-10-27 06:00 | Partial Auto Execution
35 | 20-Oct | CRQ000004373257 | 2-Significant/Large | KO | RAN-Cell | Optimization | Parametric Changes | CR for Volte BLER Parameter tuning | Completed | 48 | 48 | Completed Successfully | ZTE | 2023-10-21 | 2023-10-21 06:00 | Manual Execution
36 | 20-Oct | CRQ000004373270 | 2-Significant/Large | TN | RAN-Cell | Optimization | Corrective GPL | E// NR Anchor GPL Feature discrepancy clearance in TN Ericsson Nodes_21Oct | Completed | 962 | 1009 | Completed Partially | Ericsson | 2023-10-21 | 2023-10-21 07:00 | Partial Auto Execution
37 | 20-Oct | CRQ000004373331 | 2-Significant/Large | MH | RAN-Cell | Others | Hygiene Cleanup | TDM/IP SITE DELETION REQUIRED IN MAH | Completed | 34 | 34 | Completed Successfully | Nokia | 2023-10-20 08:00 | 2023-10-20 22:00 | Auto Execution
38 | 23-Oct | CRQ000004373350 | 2-Significant/Large | KK | RAN-Cell | Transport | Traffic Offloading | POP Migration Activity-2G | Completed |  | 50 | Completed Successfully | Huawei | 2023-10-23 23:00 | 2023-10-24 06:00 | Partial Auto Execution
39 | 23-Oct | CRQ000004373381 | 2-Significant/Large | RJ | RAN-Cell | Traffic Balancing | Traffic Migration | CR for POP traffic Shifting for 4G & 5G Nodes | Completed |  | 28 | Completed Successfully | Ericsson | 2023-10-23 11:00 | 2023-10-23 18:00 | Manual Execution
40 | 25-Oct | CRQ000004373427 | 2-Significant/Large | AS | RAN-Cell | Transport | Traffic Offloading | Global CR for Pop shifting of 2G sites | Completed |  | 40 | Completed Successfully | Ericsson | 2023-10-25 11:00 | 2023-10-25 19:00 | Manual Execution
41 | 20-Oct | CRQ000004373469 | 2-Significant/Large | WB | RAN-Cell | Optimization | Parametric Changes | Megaplexer_CTR_Building_dependent Parameter | Completed | 72 | 200 | partial done due to error in some nodes | Nokia | 2023-10-21 | 2023-10-21 06:00 | Manual Execution
42 | 20-Oct | CRQ000004373532 | 2-Significant/Large | GJ | RAN-Cell | Optimization | Parametric Changes | LTE Parameter_TTIB Enable_Independent Parameter | Completed | 731 | 729 | PARTIAL DONE DUE TO PLAN FAILED ON SOME NODES | Nokia | 2023-10-21 | 2023-10-21 06:00 | Auto Execution
43 | 26-Oct | CRQ000004373707 | 2-Significant/Large | BH | RAN-Cell | Others | Migration | 2G BTS creation and migration with NBR and Name change | Completed | 40 | 40 | Completed Successfully | Nokia | 2023-10-26 08:00 | 2023-10-27 06:00 | Auto Execution
44 | 23-Oct | CRQ000004373713 | 2-Significant/Large | RJ | RAN-Cell | Traffic Balancing | Traffic Migration | CR for POP traffic Shifting for 2G Nodes | Completed |  | 23 | Completed Successfully | Ericsson | 2023-10-23 11:00 | 2023-10-23 18:00 | Manual Execution
45 | 25-Oct | CRQ000004373742 | 2-Significant/Large | RJ | RAN-Cell | Traffic Balancing | Traffic Migration | CR for POP traffic Shifting for 4G & 5G Nodes | Completed |  | 47 | Completed Successfully | Ericsson | 2023-10-25 11:00 | 2023-10-25 18:00 | Manual Execution
46 | 26-Oct | CRQ000004373743 | 2-Significant/Large | RJ | RAN-Cell | Traffic Balancing | Traffic Migration | CR for POP traffic Shifting for 4G & 5G Nodes | Completed |  | 46 | Completed Successfully | Ericsson | 2023-10-26 11:00 | 2023-10-26 18:00 | Manual Execution
47 | 20-Oct | CRQ000004373795 | 2-Significant/Large | MU | RAN-Cell | Optimization | Parametric Changes | LTE parameter change_actArpBasedQosScaling_Independent Parameter | Completed | 1426 | 1328 | PARTIAL DONE DUE TO PLAN GETTING FAILED ON SOME NODES | Nokia | 2023-10-21 01:00 | 2023-10-21 06:00 | Auto Execution
48 | 25-Oct | CRQ000004373979 | 2-Significant/Large | BH | RAN-Cell | Optimization | Parametric Changes | LTE Parameter Change(LNCEL6)_Independent Parameter | Completed | 2028 | 1948 | Attempt All,Partial Done Due to Failed Cases | Nokia | 2023-10-26 | 2023-10-26 06:00 | Auto Execution
49 | 26-Oct | CRQ000004374107 | 2-Significant/Large | HR | RAN-Cell | Transport | Traffic Offloading | Global: 2G/4G Sites traffic shifting from one pop to another new installed link | Cancelled | 40 | 0 | Field Tester/Engineer not available | ZTE | 2023-10-26 10:00 | 2023-10-26 19:00 | Cancelled
50 | 20-Oct | CRQ000004374134 | 2-Significant/Large | BH | RAN-Cell | Optimization | Parametric Changes | Volte Parameter Change_tPingPong_Independent Parameter | Completed | 2992 | 2871 | PARTIALLY DONE DUE TO PLAN FAILED ON SOME NODES | Nokia | 2023-10-21 | 2023-10-21 06:00 | Auto Execution
51 | 20-Oct | CRQ000004374140 | 2-Significant/Large | WB | RAN-Cell | Optimization | HO/NBR Opt | CR for 2G ADCE Handover Deletion Creation | Completed | 35 | 35 | Completed Successfully | Nokia | 2023-10-21 | 2023-10-21 06:00 | Manual Execution
52 | 20-Oct | CRQ000004374182 | 2-Significant/Large | UPE | RAN-BSC/RNC | Others | Migration | UENGJ12 BSC OSS migration from UPE OSS5 to UPE OSS11 | Cancelled | 1 | 0 | Unpanned Service Interruption | Nokia | 2023-10-21 | 2023-10-21 06:00 | Cancelled
53 | 23-Oct | CRQ000004374204 | 2-Significant/Large | UPE | RAN-Cell | Others | CGI Creation/Modification | CGI Definition(Deletion Creation) in Ericsson | Completed |  | 16 | Partial completed | Ericsson | 2023-10-24 | 2023-10-24 06:00 | Manual Execution
54 | 20-Oct | CRQ000004374213 | 2-Significant/Large | MH | RAN-Cell | Optimization | Parametric Changes | LTE_parameter change_ dependent Parameter_LNCEL_tac_update | Completed | 44 | 44 | Completed Successfully | Nokia | 2023-10-21 | 2023-10-21 06:00 | Manual Execution
55 | 20-Oct | CRQ000004374239 | 2-Significant/Large | MU | RAN-Cell | Optimization | Parametric Changes | LTE parameter change_handoverAllowed_Independent Parameter | Completed | 137 | 0 | Completely failed & warning | Nokia | 2023-10-21 01:00 | 2023-10-21 06:00 | Auto Execution
56 | 20-Oct | CRQ000004374257 | 2-Significant/Large | KL | RAN-Cell | Optimization | Parametric Changes | RET Tuning in LTE Sites_ Independent Parameter | Completed | 511 | 510 | Partially done due to plan failed on few nodes | Nokia | 2023-10-20 23:00 | 2023-10-21 06:00 | Manual Execution
57 | 20-Oct | CRQ000004374288 | 2-Significant/Large | KK | RAN-Cell | Traffic Balancing | Soft Changes | L900 LMS Tuning H// Nodes | Completed |  | 2373 | Completed Successfully | Huawei | 2023-10-20 23:00 | 2023-10-21 07:00 | Manual Execution
58 | 20-Oct | CRQ000004374369 | 2-Significant/Large | OR | RAN-Cell | Optimization | Parametric Changes | LMS Tunning_ Independent Parameter | Completed | 185 | 450 | Completed Successfully | Nokia | 2023-10-21 | 2023-10-21 06:00 | Manual Execution
59 | 20-Oct | CRQ000004374371 | 2-Significant/Large | PB | RAN-Cell | Capacity Addition | New Node Addition | CGI DELETION CREATON NSA | Completed |  | 50 | Completed Successfully | Ericsson | 2023-10-21 | 2023-10-21 06:00 | Manual Execution
60 | 20-Oct | CRQ000004374377 | 1-Extensive/Widespread | BH | RAN-BSC/RNC | Traffic Balancing | Traffic Migration | GB migration from Huawei to Ericsson MME Activity_B282MUZ7 | Completed | 1 | 1 | Completed Successfully | Nokia | 2023-10-21 | 2023-10-21 06:00 | Manual Execution
61 | 20-Oct | CRQ000004374378 | 1-Extensive/Widespread | TN | RAN-BSC/RNC | Others | Migration | CBC Ips new configuration with 10.2.98.73 | Completed |  | 4 | Completed Successfully | Huawei | 2023-10-20 23:00 | 2023-10-21 06:00 | Manual Execution
62 | 20-Oct | CRQ000004374379 | 2-Significant/Large | MP | RAN-Cell | Optimization | Parametric Changes | LTE_PARAMETER_SSH_ENABLE_INDEPENDENT_PARAMETER | Completed | 3000 | 2513 | Partial Done_some Nodes Plan Failed | Nokia | 2023-10-21 | 2023-10-21 06:00 | Partial Auto Execution
63 | 20-Oct | CRQ000004374407 | 2-Significant/Large | DL | RAN-BSC/RNC | Optimization | Parametric Changes | eMLPP feature to be implemented in BSC-21Oct | Completed |  | 10 | Completed Successfully | Ericsson | 2023-10-21 | 2023-10-21 06:00 | Manual Execution
64 | 25-Oct | CRQ000004374418 | 2-Significant/Large | HR | RAN-Cell | Transport | Traffic Offloading | Global: 4G/2G Sites traffic shifting from one pop to another | Completed |  | 20 | Completed Successfully | Ericsson | 2023-10-25 10:00 | 2023-10-25 19:00 | Manual Execution
65 | 20-Oct | CRQ000004374438 | 2-Significant/Large | MH | RAN-Cell | Others | Migration | 2G site rehoming and CGI & NBR deletion and creation::MAH | Completed | 45 | 40 | PARTIALLY DONE//OMU NOT CAME UP | Nokia | 2023-10-21 | 2023-10-21 14:00 | Manual Execution
66 | 20-Oct | CRQ000004374603 | 2-Significant/Large | UPW | RAN-Cell | Optimization | PCI/RSI & Freq Change | CR_LTE Parameter_Tunning_RSI & PCI Discrepancies Removal(Ericsson) | Completed |  | 93 | Completed Partially | Ericsson | 2023-10-21 | 2023-10-21 06:00 | Partial Auto Execution
67 | 20-Oct | CRQ000004374610 | 2-Significant/Large | UPW | RAN-Cell | Optimization | HO/NBR Opt | CR_LTE Parameter_Tunning_NBR Refresh_Post RSI&PCI Change | Completed |  | 93 | Completed Partially | Ericsson | 2023-10-21 | 2023-10-21 06:00 | Partial Auto Execution
68 | 20-Oct | CRQ000004374647 | 2-Significant/Large | DL | RAN-Cell | Optimization | Parametric Changes | CR Anchor Paramter Change-4 | Completed |  | 5099 | Completed Successfully | Ericsson | 2023-10-21 | 2023-10-21 06:00 | Partial Auto Execution
69 | 23-Oct | CRQ000004374669 | 2-Significant/Large | HR | RAN-BSC/RNC | Capacity Addition | New Node Addition | Post integration of test node by ENM project team, Enrollment of test nodes GLMA01 (10.198.19.250), | Completed |  | 4 | Completed Successfully | Ericsson | 2023-10-23 10:00 | 2023-10-24 10:00 | Manual Execution
70 | 25-Oct | CRQ000004374670 | 2-Significant/Large | HR | RAN-BSC/RNC | Capacity Addition | New Node Addition | Post integration of test node by ENM project team, Enrollment of test nodes GLMA01 (10.198.19.250), | Completed | 1 | 1 | Completed Partially | Ericsson | 2023-10-25 10:00 | 2023-10-26 10:00 | Manual Execution
71 | 23-Oct | CRQ000004374738 | 2-Significant/Large | PB | RAN-Cell | Transport | Traffic Offloading | Global: 2G/4G Sites traffic shifting from one pop to another new installed link | Completed | 6 | 6 | Completed Successfully | ZTE | 2023-10-23 10:00 | 2023-10-23 20:00 | Manual Execution
72 | 20-Oct | CRQ000004374739 | 2-Significant/Large | DL | RAN-Cell | Optimization | Parametric Changes | CR for Battery Saving Parameter Modifications | Completed |  | 308 | Completed Successfully | Ericsson | 2023-10-20 12:00 | 2023-10-20 23:00 | Partial Auto Execution
73 | 20-Oct | CRQ000004374818 | 2-Significant/Large | RJ | RAN-Cell | Optimization | Parametric Changes | LTE CR for Parameter Changes (CR_PDSCHTypeBGain) | Completed |  | 4000 | Partial completed | Ericsson | 2023-10-21 | 2023-10-21 06:00 | Partial Auto Execution
74 | 25-Oct | CRQ000004374864 | 2-Significant/Large | RJ | RAN-Cell | Optimization | Parametric Changes | LTE CR for Parameter Changes (PRB Muting & Unmuting) | Completed | 1999 | 1918 | Completed Successfully | Ericsson | 2023-10-26 | 2023-10-26 06:00 | Partial Auto Execution
75 | 23-Oct | CRQ000004375134 | 2-Significant/Large | BH | RAN-Cell | Traffic Balancing | BSS Load Balancing | BCSU Balancing | Completed | 23 | 22 | PARTIALLY DONE DUE TO ONE OMU DOWN | Nokia | 2023-10-24 | 2023-10-24 06:00 | Auto Execution
76 | 23-Oct | CRQ000004375135 | 1-Extensive/Widespread | UPE | RAN-BSC/RNC | Others | Migration | UENAZM1 BSC SGSN migration from SGSN3 to vMME1 | Completed | 1 | 1 | Completed Successfully | Nokia | 2023-10-24 | 2023-10-24 06:00 | Manual Execution
77 | 25-Oct | CRQ000004375137 | 2-Significant/Large | BH | RAN-Cell | Traffic Balancing | BSS Load Balancing | BCSU Balancing | Completed | 7 | 7 | Connectivity/Tool Issue-MSDP | Nokia | 2023-10-26 | 2023-10-26 06:00 | Partial Auto Execution
78 | 25-Oct | CRQ000004375138 | 2-Significant/Large | BH | RAN-Cell | Traffic Balancing | BSS Load Balancing | BCSU Balancing | Completed | 3 | 3 | Completed Successfully | Nokia | 2023-10-26 | 2023-10-26 06:00 | Manual Execution
79 | 23-Oct | CRQ000004375164 | 2-Significant/Large | BH | RAN-Cell | Optimization | Parametric Changes | LTE parameter tune(OSS11_DLRS boost)_ Independent Parameter | Completed | 2330 | 2291 | Partially done due to plan failed on few nodes | Nokia | 2023-10-24 | 2023-10-24 06:00 | Manual Execution
80 | 26-Oct | CRQ000004375183 | 2-Significant/Large | DL | RAN-Cell | Transport | IP Addition | 4G and 5G site/POP Shifting | Completed |  | 50 | Completed Successfully | Ericsson | 2023-10-26 10:00 | 2023-10-26 23:00 | Manual Execution
81 | 23-Oct | CRQ000004375229 | 2-Significant/Large | GJ | RAN-Cell | Others | Migration | Site Creation_BSC01AHD & BS166GOD_23-Oct_1 | Completed | 40 | 40 | Completed Successfully | Nokia | 2023-10-23 08:00 | 2023-10-23 22:00 | Manual Execution
82 | 23-Oct | CRQ000004375300 | 2-Significant/Large | JK | RAN-Cell | Optimization | Parametric Changes | 4G_TransportQoS JK | Completed |  | 93 | Completed Partially | Ericsson | 2023-10-24 | 2023-10-24 06:00 | Partial Auto Execution
83 | 23-Oct | CRQ000004375335 | 2-Significant/Large | BH | RAN-Cell | Others | ZQ removal of New Sites | Name Change_2G | Completed | 80 | 87 | Completed Successfully | Nokia | 2023-10-23 23:00 | 2023-10-24 06:00 | Auto Execution
84 | 23-Oct | CRQ000004375353 | 1-Extensive/Widespread | MH | RAN-BSC/RNC | Capacity Addition | New Node Addition | New BCSU-3 addition in BSC146PAH | Cancelled | 1 | 0 | Unpanned Service Interruption | Nokia | 2023-10-24 | 2023-10-24 06:00 | Cancelled
85 | 23-Oct | CRQ000004375433 | 2-Significant/Large | MH | RAN-Cell | Traffic Balancing | Traffic Migration | MH MRBTS OSS MIGRATION SBTS SITES & SITE NAME CHANGE | Completed | 200 | 198 | Partially Done//Plan Got Failed on some Nodes | Nokia | 2023-10-24 | 2023-10-24 06:00 | Manual Execution
86 | 23-Oct | CRQ000004375435 | 2-Significant/Large | BH | RAN-Cell | Optimization | Parametric Changes | LTE parameter tune(ULS_EARFCN)_ Dependent Parameter | Completed | 226 | 204 | Partially done due to plan failed on few nodes | Nokia | 2023-10-24 | 2023-10-24 06:00 | Auto Execution
87 | 23-Oct | CRQ000004375438 | 2-Significant/Large | UPE | RAN-BSC/RNC | Others | Migration | UENVRN8 BSC OSS migration from UPE OSS5 to UPE OSS9 | Completed | 1 | 1 | Completed Successfully | Nokia | 2023-10-24 | 2023-10-24 06:00 | Manual Execution
88 | 26-Oct | CRQ000004375440 | 2-Significant/Large | UPE | RAN-Cell | Others | Migration | Nokia_Site Creation | Completed | 40 | 40 | Completed Successfully | Nokia | 2023-10-26 10:00 | 2023-10-26 23:00 | Manual Execution
89 | 26-Oct | CRQ000004375448 | 2-Significant/Large | BH | RAN-Cell | Optimization | Parametric Changes | LTE Parameter Change(LNBTS)_Independent Parameter | Completed | 2221 | 2159 | Attempt All,Partial Done Due to Failed Cases | Nokia | 2023-10-27 | 2023-10-27 06:00 | Auto Execution
90 | 23-Oct | CRQ000004375492 | 2-Significant/Large | BH | RAN-Cell | Optimization | Parametric Changes | Volte Parameter Change_LMS Retune_Independent Parameter | Completed | 1684 | 1556 | Partially done due to plan failed on few nodes | Nokia | 2023-10-24 | 2023-10-24 06:00 | Manual Execution
91 | 25-Oct | CRQ000004375505 | 2-Significant/Large | DL | RAN-Cell | Transport | IP Addition | 4G site/POP Shifting | Completed |  | 50 | Completed Successfully | Ericsson | 2023-10-25 10:00 | 2023-10-25 23:00 | Manual Execution
92 | 26-Oct | CRQ000004375526 | 2-Significant/Large | UPW | RAN-Cell | Transport | IP Addition | 4G And 2G Sites POP Shifting in Ericsson Node | Completed |  | 59 | Completed Successfully | Ericsson | 2023-10-26 10:00 | 2023-10-26 22:00 | Manual Execution
93 | 24-Oct | CRQ000004375587 | 2-Significant/Large | AP | RAN-Cell | Swap or Modernisation | Modernisation | GSM900 Harmonization Inconsistent CR for 38sites | Completed |  | 38 | Completed Successfully | Ericsson | 2023-10-24 10:00 | 2023-10-24 18:00 | Manual Execution
94 | 23-Oct | CRQ000004375600 | 2-Significant/Large | PB | RAN-Cell | Capacity Addition | New Node Addition | CGI DELETION CREATON NSA | Completed |  | 50 | Completed Successfully | Ericsson | 2023-10-24 | 2023-10-24 06:00 | Manual Execution
95 | 23-Oct | CRQ000004375780 | 2-Significant/Large | UPW | RAN-Cell | Transport | QOS | 5G_Readyness_CR_LTE Parameter_Tunning_QOS Parameter | Completed |  | 467 | Completed Successfully | Huawei | 2023-10-24 | 2023-10-24 06:00 | Manual Execution
96 | 25-Oct | CRQ000004375784 | 2-Significant/Large | UPW | RAN-Cell | Traffic Balancing | Soft Changes | CR_LTE Parameter_Tunning_LMS Parameter | Completed |  | 1426 | Completed Successfully | Huawei | 2023-10-26 | 2023-10-26 06:00 | Manual Execution
97 | 25-Oct | CRQ000004375786 | 2-Significant/Large | UPW | RAN-Cell | Traffic Balancing | Soft Changes | CR_LTE Parameter_Tunning_LMS Parameter_Ericsson | Completed | 15 | 14 | partial completed | Ericsson | 2023-10-26 | 2023-10-26 06:00 | Manual Execution
98 | 23-Oct | CRQ000004376259 | 2-Significant/Large | MP | RAN-Cell | Optimization | Parametric Changes | HOC & POC PARAMETERdlPcPowerReductiondlPcWindowSizepcControlIntervalenaFastAveCallSetup , | Completed | 1000 | 120 | PARTIAL DONE DUE TO PLAN GETTING FAILED ON SOME NODES | Nokia | 2023-10-24 | 2023-10-24 06:00 | Auto Execution
99 | 23-Oct | CRQ000004376262 | 2-Significant/Large | AP | RAN-Cell | Optimization | Parametric Changes | 5G RAN Parameter changes 2000 Nodes SA Activity | Completed |  | 2000 | Completed Successfully | Ericsson | 2023-10-24 | 2023-10-24 06:00 | Partial Auto Execution
100 | 23-Oct | CRQ000004376264 | 2-Significant/Large | UPE | RAN-Cell | Capacity Addition | Soft TRX Addition | Soft TRX_BTS Grow | Completed | 125 | 69 | PARTIAL DONE DUE TO PLAN FAILED ON SOME NODES | Nokia | 2023-10-24 | 2023-10-24 06:00 | Manual Execution
101 | 25-Oct | CRQ000004376710 | 2-Significant/Large | KK | RAN-BSC/RNC | Capacity Addition | New Node Addition | Test Node Integration for New KKENM2 testing (KK-LDSTHL1-2 and | Completed |  | 1 | Completed Successfully | Ericsson | 2023-10-25 22:00 | 2023-10-26 22:00 | Manual Execution
102 | 23-Oct | CRQ000004376735 | 2-Significant/Large | DL | RAN-BSC/RNC | Optimization | Parametric Changes | eMLPP feature to be implemented in BSC-24Oct | Completed | 3 | 3 | Completed Successfully | Ericsson | 2023-10-24 | 2023-10-24 06:00 | Manual Execution
103 | 25-Oct | CRQ000004376754 | 2-Significant/Large | MP | RAN-Cell | Others | Migration | 2G SRAN Site CGI Creation & Deletion in MSS4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22 | Completed |  | 106 | Completed Successfully | Nokia | 2023-10-25 11:00 | 2023-10-25 19:00 | Auto Execution
104 | 25-Oct | CRQ000004377235 | 2-Significant/Large | AP | RAN-Cell | Swap or Modernisation | Modernisation | GSM900 Implementation required in 38 Site at Cell level. | Completed |  | 38 | Completed Successfully | Ericsson | 2023-10-25 23:00 | 2023-10-26 06:00 | Manual Execution
105 | 23-Oct | CRQ000004377268 | 2-Significant/Large | CH | RAN-Cell | Optimization | Parametric Changes | 4G E// MLB Change 1713 node | Completed |  | 1713 | Completed Successfully | Ericsson | 2023-10-24 | 2023-10-24 06:00 | Partial Auto Execution
106 | 23-Oct | CRQ000004377979 | 2-Significant/Large | GJ | RAN-Cell | Others | Migration | Site Migration, Modification, CGI & NBR Definition_24 Oct_1 | Completed | 40 | 15 | Partial Done_Due to Media Issue | Nokia | 2023-10-24 | 2023-10-24 06:00 | Manual Execution
107 | 23-Oct | CRQ000004378142 | 2-Significant/Large | JK | RAN-Cell | Optimization | Parametric Changes | 4G_Parameter(CRS) tuning in JK | Completed |  | 192 | Completed Successfully | Ericsson | 2023-10-24 | 2023-10-24 06:00 | Partial Auto Execution
108 | 23-Oct | CRQ000004378417 | 2-Significant/Large | KK | RAN-Cell | Traffic Balancing | Power Changes | L900 - Power Boosting_UL MG Improvement | Completed |  | 266 | Completed Successfully | Huawei | 2023-10-23 23:00 | 2023-10-24 07:00 | Manual Execution
109 | 25-Oct | CRQ000004378455 | 2-Significant/Large | BH | RAN-Cell | Optimization | Parametric Changes | LTE parameter tune(LNCEL_TDD_dlrsboost)_ Independent Parameter | Cancelled |  | 3000 | Planning/Design Gap-Ericsson | Nokia | 2023-10-26 | 2023-10-26 06:00 | Cancelled
110 | 26-Oct | CRQ000004378486 | 2-Significant/Large | TN | RAN-Cell | Optimization | Parametric Changes | E// CA Deactivation in_L2100 Layer for TN Ericsson Nodes_27Oct | Completed |  | 600 | Completed Successfully | Ericsson | 2023-10-27 | 2023-10-27 07:00 | Partial Auto Execution
111 | 25-Oct | CRQ000004380750 | 2-Significant/Large | GJ | RAN-Cell | Optimization | Parametric Changes | LTE parameter change_LNCEL_Independent Parameter | Completed | 2578 | 2434 | Partial Done_some Nodes Plan Failed | Nokia | 2023-10-26 | 2023-10-26 06:00 | Auto Execution
112 | 26-Oct | CRQ000004380877 | 2-Significant/Large | MU | RAN-Cell | Optimization | Parametric Changes | LTE parameter change_LMS-Opti_Independent Parameter | Completed | 18 | 18 | Partially done due to plan failed on few nodes | Nokia | 2023-10-27 01:00 | 2023-10-27 06:00 | Auto Execution
113 | 25-Oct | CRQ000004381122 | 2-Significant/Large | HP | RAN-Cell | Optimization | Parametric Changes | 2G - eMLPP Feature implementation | Completed | 3 | 3 | Completed Successfully | Ericsson | 2023-10-26 | 2023-10-26 06:00 | Manual Execution
114 | 26-Oct | CRQ000004381516 | 2-Significant/Large | RJ | RAN-Cell | Traffic Balancing | Soft Changes - 5G | 5G_readiness CR for Parameter Change (Ericsson)(5G_TermPoint2GnbBlockDGraterThan200PSSessionFailure) | Completed | 3939 | 3921 | Completed Partial | Ericsson | 2023-10-27 | 2023-10-27 06:00 | Partial Auto Execution
115 | 25-Oct | CRQ000004381533 | 2-Significant/Large | OR | RAN-Cell | Optimization | Parametric Changes | LMS Tunning_ Independent Parameter | Completed | 75 | 75 | Completed Successfully | Nokia | 2023-10-26 | 2023-10-26 06:00 | Auto Execution
116 | 25-Oct | CRQ000004381535 | 2-Significant/Large | OR | RAN-Cell | Others | Site Nomenclature Change | 5G CELL RENAME_ Independent Parameter | Completed | 92 | 88 | Partially done due to fail case | Nokia | 2023-10-26 | 2023-10-26 06:00 | Auto Execution
117 | 25-Oct | CRQ000004381562 | 2-Significant/Large | MP | RAN-Cell | Capacity Addition | Soft TRX Addition | Trx Creation and Working | Completed | 68 | 18 | PARTIALLY DONE DUE TO PLAN FAILED ON SOME BTS | Nokia | 2023-10-26 | 2023-10-26 06:00 | Manual Execution
118 | 25-Oct | CRQ000004381566 | 2-Significant/Large | DL | RAN-Cell | Optimization | Parametric Changes | CR CA Activate L1800 to TDD | Completed |  | 3801 | Completed Successfully | Ericsson | 2023-10-26 | 2023-10-26 06:00 | Partial Auto Execution
119 | 26-Oct | CRQ000004381583 | 2-Significant/Large | AP | RAN-Cell | Swap or Modernisation | Modernisation | BSC level parameter -MSQUEUING&MSQHOPRIO to be change in 76BSC's | Completed | 76 | 76 | Completed Successfully | Ericsson | 2023-10-27 | 2023-10-27 06:00 | Manual Execution
120 | 25-Oct | CRQ000004381752 | 2-Significant/Large | UPE | RAN-Cell | Capacity Addition | Soft TRX Addition | Soft TRX_BTS Grow | Completed | 125 | 71 | PARTIAL DONE DUE TO PLAN FAILED ON SOME NODES | Nokia | 2023-10-26 | 2023-10-26 06:00 | Manual Execution
121 | 26-Oct | CRQ000004381755 | 2-Significant/Large | HP | RAN-Cell | Transport | Traffic Offloading | Global: 4G/2G Sites traffic shifting from one pop to another | Cancelled |  | 20 | Planning/Design Gap-Ericsson | Ericsson | 2023-10-26 10:00 | 2023-10-26 19:00 | Cancelled
122 | 25-Oct | CRQ000004381839 | 2-Significant/Large | JK | RAN-Cell | Optimization | Parametric Changes | 4G_CRS tuning in JK | Completed | 711 | 705 | Completed Successfully | Ericsson | 2023-10-26 | 2023-10-26 06:00 | Partial Auto Execution
123 | 26-Oct | CRQ000004382028 | 2-Significant/Large | OR | RAN-Cell | Optimization | HO/NBR Opt | 2G_Neighour Optimization | Completed | 1486 | 1486 | Completed Successfully | Nokia | 2023-10-26 08:00 | 2023-10-26 17:00 | Manual Execution
124 | 26-Oct | CRQ000004382040 | 2-Significant/Large | MH | RAN-Cell | Optimization | Parametric Changes | LTE_parameter change_ independent Parameter_LNHOIF_update | Completed | 569 | 575 | Completed Successfully | Nokia | 2023-10-27 | 2023-10-27 06:00 | Auto Execution
125 | 25-Oct | CRQ000004382145 | 2-Significant/Large | MP | RAN-Cell | Optimization | Parametric Changes | BTSPARAMETERbtsIsHoppingdtmEnableddtxModefastReturnToLTEgsmPrioritymaxTimeLimitDirectedRe | Completed | 181 | 181 | Completed Successfully | Nokia | 2023-10-26 | 2023-10-26 06:00 | Auto Execution
126 | 25-Oct | CRQ000004382155 | 1-Extensive/Widespread | BH | RAN-BSC/RNC | Traffic Balancing | Traffic Migration | GB migration from Huawei to Ericsson MME Activity_B336MUZ21 | Completed | 1 | 1 | Completed Successfully | Nokia | 2023-10-26 | 2023-10-26 06:00 | Manual Execution
127 | 26-Oct | CRQ000004382284 | 2-Significant/Large | JK | RAN-Cell | Optimization | Term Point Correction-5G | 5G_JK_Termpoint2gNB Addition IP Change | Completed | 153 | 153 | Completed Successfully | Ericsson | 2023-10-27 | 2023-10-27 06:00 | Manual Execution
128 | 26-Oct | CRQ000004382287 | 2-Significant/Large | GJ | RAN-Cell | Optimization | Parametric Changes | LTE Parameter Change_LNCEL_Independent Parameter | Completed | 2200 | 2133 | PARTIALLY DONE DUE TO PLAN FAILED ON SOME NODES | Nokia | 2023-10-27 | 2023-10-27 06:00 | Auto Execution
129 | 26-Oct | CRQ000004382536 | 2-Significant/Large | GJ | RAN-Cell | Others | Migration | 2G VLAN change for MPLS migration | Completed | 90 | 95 | Completed Successfully | Nokia | 2023-10-27 | 2023-10-27 06:00 | Manual Execution
130 | 26-Oct | CRQ000004382615 | 2-Significant/Large | GJ | RAN-Cell | Optimization | Parametric Changes | LTE_Parameter Change_4G-5G_X2_Optimization_dependent parameter | Completed | 3000 | 2518 | PARTIALLY DONE DUE TO PLAN FAILED ON SOME NODES | Nokia | 2023-10-27 | 2023-10-27 06:00 | Manual Execution
131 | 26-Oct | CRQ000004382623 | 2-Significant/Large | GJ | RAN-Cell | Traffic Balancing | Power Changes | pMax Tuning Activity_Independent Parameter | Completed | 2200 | 279 | PARTIALLY DONE DUE TO PLAN FAILED ON SOME NODES | Nokia | 2023-10-27 | 2023-10-27 06:00 | Manual Execution
132 | 27-Oct | CRQ000004382733 | 2-Significant/Large | MU | RAN-Cell | Others | Site Nomenclature Change | LTE Cell Name Change | Completed | 150 | 150 | Completed Successfully | Nokia | 2023-10-27 07:00 | 2023-10-27 23:00 | Manual Execution
133 | 26-Oct | CRQ000004382766 | 2-Significant/Large | MH | RAN-Cell | Optimization | Parametric Changes | LTE parameter change_Independent Parameter_LNBTS_rrcGAURDtimer_update | Completed | 2500 | 3050 | Completed Successfully | Nokia | 2023-10-27 | 2023-10-27 06:00 | Auto Execution
134 | 26-Oct | CRQ000004382781 | 2-Significant/Large | KL | RAN-Cell | Optimization | Soft Opt. TAC/LAC | ADCE Neighbour Deletion Creation | Completed | 6200 | 6111 | Partially Done//Plan Got Failed on some Nodes | Nokia | 2023-10-27 | 2023-10-27 06:00 | Manual Execution
135 | 26-Oct | CRQ000004382789 | 2-Significant/Large | KL | RAN-Cell | Optimization | Parametric Changes | GPL correction in LTE sites_ Independent Parameter | Completed | 1080 | 1002 | Partial Done_some Nodes Plan Failed | Nokia | 2023-10-26 23:00 | 2023-10-27 06:00 | Manual Execution
136 | 26-Oct | CRQ000004382919 | 2-Significant/Large | JK | RAN-Cell | Optimization | Parametric Changes | 2G_CR_CGI Definition | Completed | 4 | 3 | Partially completed | Ericsson | 2023-10-27 | 2023-10-27 06:00 | Manual Execution
137 | 26-Oct | CRQ000004382924 | 2-Significant/Large | GJ | RAN-Cell | Traffic Balancing | BSS Load Balancing | ETPE Balancing in BS139RJT | Completed | 146 | 146 | Completed Successfully | Nokia | 2023-10-27 | 2023-10-27 06:00 | Manual Execution
138 | 26-Oct | CRQ000004383048 | 2-Significant/Large | MU | RAN-Cell | Optimization | Corrective GPL | LTE PARAMETER CHANGE_GPL NR-Deviation correction_Independent Parameter | Completed | 1587 | 750 | Partially done due to plan failed on few nodes | Nokia | 2023-10-27 01:00 | 2023-10-27 06:00 | Auto Execution
139 | 26-Oct | CRQ000004383095 | 2-Significant/Large | KO | RAN-Cell | Optimization | Parametric Changes | CR for Volte HARQ Parameter tuning | Completed | 20 | 20 | Completed Successfully | ZTE | 2023-10-27 | 2023-10-27 06:00 | Manual Execution
140 | 26-Oct | CRQ000004383100 | 2-Significant/Large | WB | RAN-Cell | Optimization | Parametric Changes | LTE Parameter Change_(inactivityTimer)_Independent_parameter | Completed | 601 | 1135 | partial done due to error in some nodes | Nokia | 2023-10-26 23:00 | 2023-10-27 06:00 | Auto Execution
141 | 26-Oct | CRQ000004383119 | 2-Significant/Large | BH | RAN-Cell | Optimization | Parametric Changes | POC parameter change | Completed | 3160 | 3033 | Partial Done_some Nodes Plan Failed | Nokia | 2023-10-27 | 2023-10-27 06:00 | Auto Execution
142 | 27-Oct | CRQ000004383194 | 2-Significant/Large | MH | RAN-Cell | Others | Migration | 2G SITE CREATION REQUIRED FOR REHOMING ¦BSC DISMANTLE:MAH | Cancelled | 45 | 0 | Planning/Design Gap-Ericsson | Nokia | 2023-10-27 08:00 | 2023-10-27 22:00 | Cancelled
143 | 26-Oct | CRQ000004383197 | 2-Significant/Large | BH | RAN-Cell | Others | ZQ removal of New Sites | Name Change_2G | Completed | 79 | 70 | Partially Done due to failed cases | Nokia | 2023-10-26 23:00 | 2023-10-27 23:00 | Auto Execution
144 | 26-Oct | CRQ000004383200 | 2-Significant/Large | BH | RAN-Cell | Optimization | Parametric Changes | LTE parameter tune(IFLB)_ Independent Parameter | Completed | 1395 | 1258 | Attempt All,Partial Done Due to Failed Cases | Nokia | 2023-10-27 | 2023-10-27 06:00 | Auto Execution
145 | 27-Oct | CRQ000004383212 | 2-Significant/Large | OR | RAN-Cell | Others | Hygiene Cleanup | UNUSED LAPD & ASSOCIATION DELETE | Completed | 451 | 451 | Completed Successfully | Nokia | 2023-10-27 08:00 | 2023-10-27 17:00 | Manual Execution
146 | 27-Oct | CRQ000004383233 | 2-Significant/Large | MH | RAN-Cell | Others | Migration | 2G SITE CREATION REQUIRED FOR REHOMING ¦BSC DISMANTLE:MAH | Cancelled | 45 | 0 | Planning/Design Gap-Ericsson | Nokia | 2023-10-27 08:00 | 2023-10-27 22:00 | Cancelled
147 | 26-Oct | CRQ000004383246 | 2-Significant/Large | HR | RAN-Cell | Capacity Addition | Soft TRX Addition | TRX Grow & PA Balancing (Addition/Deletion) | Completed | 268 | 73 | Partial Done due to time constraint | ZTE | 2023-10-27 | 2023-10-27 06:00 | Manual Execution
148 | 26-Oct | CRQ000004383250 | 2-Significant/Large | HP | RAN-Cell | Optimization | Parametric Changes | 2G eMLPP Feature implementation | Cancelled |  | 5 |  | Ericsson | 2023-10-27 | 2023-10-27 06:00 | Cancelled
149 | 26-Oct | CRQ000004383269 | 2-Significant/Large | KO | RAN-Cell | Optimization | Parametric Changes | CR for LMS Modification (Nokia) | Completed | 162 | 164 | partial done due to error in some nodes | Nokia | 2023-10-27 | 2023-10-27 06:00 | Manual Execution
150 | 26-Oct | CRQ000004383312 | 2-Significant/Large | UPE | RAN-Cell | Others | CGI Creation/Modification | CGI Definition(Creation) in Ericsson | Completed |  | 16 | Completed Successfully | Ericsson | 2023-10-27 | 2023-10-27 06:00 | Manual Execution
151 | 26-Oct | CRQ000004383318 | 2-Significant/Large | BH | RAN-Cell | Optimization | Parametric Changes | LTE Parameter Change(LNBTS2)_Independent Parameter | Completed | 2078 | 2004 | Attempt All,Partial Done Due to Failed Cases | Nokia | 2023-10-27 | 2023-10-27 06:00 | Auto Execution
152 | 26-Oct | CRQ000004383375 | 2-Significant/Large | RJ | RAN-Cell | Optimization | Parametric Changes | LTE CR for Cellreslectionprio & ConnectedmodePrio_P1 | Completed |  | 3966 | Completed Partially | Ericsson | 2023-10-27 | 2023-10-27 06:00 | Partial Auto Execution
153 | 26-Oct | CRQ000004383386 | 1-Extensive/Widespread | BH | RAN-BSC/RNC | Traffic Balancing | Traffic Migration | GB migration from Huawei to Ericsson MME Activity_B177BHB1 | Completed | 1 | 1 | Completed Successfully | Nokia | 2023-10-27 | 2023-10-27 06:00 | Manual Execution
154 | 26-Oct | CRQ000004383400 | 2-Significant/Large | MP | RAN-Cell | Optimization | Parametric Changes | BCF PARAMETER(T200S & T200F) | Completed | 364 | 362 | Completed Successfully | Nokia | 2023-10-27 | 2023-10-27 06:00 | Manual Execution
155 | 26-Oct | CRQ000004383427 | 2-Significant/Large | KL | RAN-Cell | Optimization | Parametric Changes | MTU Size standardization at Enodeb _ Independent Parameter | Completed | 1500 | 1490 | Partial Done_some Nodes Plan Failed | Nokia | 2023-10-27 | 2023-10-27 06:00 | Manual Execution
156 | 26-Oct | CRQ000004383432 | 2-Significant/Large | UPE | RAN-BSC/RNC | Others | Migration | UENKN07 BSC OSS migration from UPE OSS4 to UPE OSS11 | Completed | 1 | 1 | Completed Successfully | Nokia | 2023-10-27 | 2023-10-27 06:00 | Manual Execution
157 | 26-Oct | CRQ000004383465 | 2-Significant/Large | MP | RAN-Cell | Optimization | Parametric Changes | LTE_PARAMETER_CHANGE_LNADJGNB_UPDATE_INDEPENDENT_PARAMETER | Completed | 144 | 136 | Completed Successfully | Nokia | 2023-10-27 | 2023-10-27 06:00 | Manual Execution
158 | 26-Oct | CRQ000004383473 | 2-Significant/Large | KK | RAN-Cell | Traffic Balancing | Soft Changes | Ping-Pong Ho Reduction H// Nodes | Completed | 6112 | 6112 | Completed Successfully | Huawei | 2023-10-26 23:00 | 2023-10-27 07:00 | Manual Execution
159 | 26-Oct | CRQ000004383488 | 1-Extensive/Widespread | KL | RAN-BSC/RNC | Transport | IP Addition | Static Route addition and deletion in EKMNBS1 with BOX sych | Completed | 1 | 1 | Completed Successfully | Nokia | 2023-10-27 | 2023-10-27 06:00 | Partial Auto Execution
160 | 26-Oct | CRQ000004383512 | 2-Significant/Large | RJ | RAN-Cell | Optimization | Parametric Changes | LTE CR for Cellreslectionprio & ConnectedmodePrio_P0 | Completed |  | 3971 | Completed Partially | Ericsson | 2023-10-27 | 2023-10-27 06:00 | Partial Auto Execution
161 | 26-Oct | CRQ000004383619 | 2-Significant/Large | DL | RAN-Cell | Optimization | Parametric Changes | CR Anchor Paramter Change-5 | Completed | 4001 | 3767 | Completed Partially | Ericsson | 2023-10-27 | 2023-10-27 06:00 | Partial Auto Execution
162 | 26-Oct | CRQ000004383622 | 2-Significant/Large | MP | RAN-Cell | Optimization | Parametric Changes | LTE IFLB Parameter change_Independent Parameter | Completed | 3000 | 982 | Completed Successfully | Nokia | 2023-10-27 | 2023-10-27 06:00 | Manual Execution
163 | 26-Oct | CRQ000004383691 | 2-Significant/Large | DL | RAN-Cell | Optimization | Parametric Changes | RSSI Mitigation Trial_27-Oct'23 | Completed |  | 414 | Completed Successfully | Ericsson | 2023-10-27 | 2023-10-27 06:00 | Partial Auto Execution

## Dashboard
S.No | Domain | Successful CR Count | CR Done by Automation | Automation % | Node touch of successful CR | MOP Visited for Successful CR | MOP Visited % | Cancelled CR | Reverted CR
1 | RAN_Nokia | 79 | 31 | 39 | 71411 | 79 | 100 | 5 | 0
2 | RAN_ZTE | 4 | 0 | 0 | 342 | 4 | 100 | 1 | 0
3 | RAN_ERICSSON | 59 | 22 | 37 | 12609 | 59 | 100 | 2 | 0
4 | RAN_HUAWEI | 13 | 2 | 15 | 6282 | 13 | 100 | 0 | 0